## Multi-day Conference Timeline
Planning Timeline for Multi-day Conference
Committee:
Title of Event:
Proposed Event Start Date: |  |  |  | (MM/DD/YY) | Event End Date:
Location type for Seminar: |  |  | Contract space (Hotel or conference center) |  |  | Free space (Utility/Consultant or donated space)
Registration Fee: |  | (member fee) |  | Target Attendance:
(non-member fee)
Goal Net Income*: | 0
* 25% of revenue generated - rough budget projection only. Use budget spreadsheet for final predictions
Task |  |  |  |  | Target Range |  | Due Date | Assigned Committee Member
9-12 Months out
Select date (Check Section calendar to verify no conflicts) |  |  |  |  | 12 | months | -360
Determine location (contract vs. free) |  |  |  |  | 12 | months | -360
Negotiate any contracts for Room rental, AV, Lodging (if applicable) |  |  |  |  | 10.5 | months | -315
Select caterer and negotiate contract (if different then facility) |  |  |  |  | 10.5 | months | -315
Send all contract to Association for signature |  |  |  |  | 10 | months | -300
6-9 Months out
Determine Topic |  |  |  |  | 9 | months | -270
Confirm Speakers/Presenters |  |  |  |  | 8 | months | -240
Receive abstracts from speakers |  |  |  |  | 7 | months | -210
Submit joint CPE form for consideration |  |  |  |  | 6 | months | -180
3-6 Months out
Prepare draft flyer/brochure |  |  |  |  | 5 | months | -150
Send information to Executive Director for registration site and conduct testing |  |  |  |  | 5 | months | -150
Receive CPE approvals |  |  |  |  | 4.5 | months | -135
Finalize flyer/brochure and open registration |  |  |  |  | 4 | months | -120
Promote event via e-Newsletter, Magazine, Website, Social Media |  |  |  |  | 4 | months | -120
Mail flyers (if applicable) |  |  |  |  | 4 | months | -120
Monitor registration and continue to promote event |  |  |  |  | 3 | months | -90
1-2 Months out
Re-confirm local arrangements |  |  |  |  | 2 | months | -60
Assign moderator/volunteer positions for on-site tasks |  |  |  |  | 1 | month | -30
Confirm AV needs/equipment |  |  |  |  | 1 | month | -30
Receive presentations from speakers |  |  |  |  | 1 | month | -30
2 Weeks out
Print agenda/handouts |  |  |  |  | 2 | weeks | -14
Acquire Speaker Bios for introductions |  |  |  |  | 2 | weeks | -14
1 Week out
Send final attendee numbers to caterer |  |  |  |  | 1 | week | -7
Receive any registration materials from Exec Director if unable to attend |  |  |  |  | 1 | week | -7
Link to Eventfull App sent to volunteers for scanning |  |  |  |  | 1 | week | -7
Day of Seminar
Ensure volunteers fulfill their assigned duties | [6 empty] | 0
Conduct mini-training with volunteers in charge of scanning duties | [6 empty] | 0
Review and sign any location/catering charge for seminar | [6 empty] | 0
After the Seminar
Confirm with Executive Director there were no changes to program and all badges were properly scanned |  |  |  |  | 1 | week | 1900-01-06
Submit Invoice Payment Requests for all expenses |  |  |  |  | 1 | week | 1900-01-06
Send final presentations and event photos to Exec Director for posting online |  |  |  |  | 1 | week | 1900-01-06
Send Thank you notes to speakers |  |  |  |  | 1 | week | 1900-01-06
Formulas:
Due Date = C5-([Target Range]*30)
Due Date = C5+([Target Range]*7)

## One-day Seminar Timeline
Planning Timeline for One-day Seminar
Committee:
Title of Event:
Proposed Event Date: |  |  | (MM/DD/YY)
Location type for Seminar: |  | Contract space (Hotel or conference center) |  |  | Free space (Utility/Consultant or donated space)
Registration Fee: | (member fee) |  | Target Attendance:
(non-member fee)
Budget/Projected Net Income*: |  | 0
* 25% of revenue generated - rough budget projection only. Use budget spreadsheet for final predictions
Task |  |  |  | Target Range |  | Due Date | Assigned Committee Member
6-9 Months out
Select date (Check Section calendar to verify no conflicts) |  |  |  | 9 | months | -270
Determine location (contract vs. free) |  |  |  | 9 | months | -270
Negotiate any contracts for Room rental, AV, Lodging (if applicable) |  |  |  | 8 | months | -240
Select caterer and negotiate contract (if different then facility) |  |  |  | 8 | months | -240
Send all contracts to Association for signature |  |  |  | 8 | months | -240
Determine Topic |  |  |  | 8 | months | -240
Confirm Speakers/Presenters |  |  |  | 7 | months | -210
Receive abstracts from speakers |  |  |  | 6.25 | months | -187.5
Submit joint CPE form for consideration |  |  |  | 6 | months | -180
3-6 Months out
Prepare draft flyer/brochure |  |  |  | 5 | months | -150
Send information to Exec Director for registration site and conduct testing |  |  |  | 5 | months | -150
Receive CPE approvals |  |  |  | 4.5 | months | -135
Finalize flyer/brochure and open registration |  |  |  | 4 | months | -120
Promote event via e-Newsletter, Magazine, Website, Social Media |  |  |  | 4 | months | -120
Mail flyers (if applicable) |  |  |  | 4 | months | -120
Monitor registration and continue to promote event |  |  |  | 3 | months | -90
1-2 Months out
Re-confirm local arrangements |  |  |  | 2 | months | -60
Assign moderator/volunteer positions for on-site tasks |  |  |  | 1 | month | -30
Confirm AV needs/equipment |  |  |  | 1 | month | -30
Receive presentations from speakers |  |  |  | 1 | month | -30
2 Weeks out
Print agenda/handouts |  |  |  | 2 | weeks | -14
Acquire Speaker Bios for introductions |  |  |  | 2 | weeks | -14
1 Week out
Send final attendee numbers to caterer |  |  |  | 1 | week | -7
Receive any registration materials from Exec Director if unable to attend |  |  |  | 1 | week | -7
Link to Eventfull App sent to volunteers for scanning |  |  |  | 1 | week | -7
Day of Seminar
Ensure volunteers fulfill their assigned duties | [5 empty] | 0
Conduct mini-training with volunteers in charge of scanning duties | [5 empty] | 0
Review and sign any location/catering charge for seminar | [5 empty] | 0
After the Seminar
Confirm with Executive Director there were no changes to program and all badges were properly scanned |  |  |  | 1 | week | 1900-01-06
Submit Invoice Payment Requests for all expenses |  |  |  | 1 | week | 1900-01-06
Send final presentations and event photos to Exec Director for posting online |  |  |  | 1 | week | 1900-01-06
Send Thank you notes to speakers |  |  |  | 1 | week | 1900-01-06
Formulas:
Due Date = C5-([Target Range]*30)
Due Date = C5+([Target Range]*7)

## Webinar Timeline
Planning Timeline for Webinars
Committee:
Title of Event:
Proposed Event Date: |  |  | (MM/DD/YY)
Determine type of webinar: |  | Site locations | Online Only |  | Hybrid
Registration Fee: | (member fee) |  | Target Attendance:
(non-member fee)
Finalize Budget/Projected Net Income (Using site locations): |  |  |  | 0
Finalize Budget/Projected Net Income (Online Only): |  |  |  | 0
Task |  |  |  | Target Range |  | Due Date | Assigned Committee Member
3-6 Months out
Determine Topic |  |  |  | 6 | months | -180
Confirm Speakers/Presenters |  |  |  | 5.25 | months | -157.5
Receive abstracts from speakers |  |  |  | 4.5 | months | -135
Site locations contacted to confirm availability (if applicable) |  |  |  | 4 | months | -120
Submit joint CPE form for consideration |  |  |  | 4 | months | -120
Prepare flyer/brochure |  |  |  | 3.5 | months | -105
Create registration site and conduct testing |  |  |  | 3.5 | months | -105
2-3 Months out
Receive CPE approvals |  |  |  | 3 | months | -90
Open registration |  |  |  | 3 | months | -90
Promote event via e-Newsletter, Magazine, website |  |  |  | 3 | months | -90
Mail flyers (if applicable) |  |  |  | 2.5 | months | -75
Create webinar powerpoint template for use by speakers |  |  |  | 2.5 | months | -75
1-2 Months out
Re-confirm local arrangements (if applicable) |  |  |  | 2 | months | -60
Schedule Test run with speakers |  |  |  | 1 | month | -30
Schedule Test run with site locations |  |  |  | 1 | month | -30
Receive post-test questions from Speakers (Required if CPE's approved) |  |  |  | 1 | month | -30
Create post-test for online attendees (Required if CPE's approved) |  |  |  | 1 | month | -30
2 Weeks out
Send out Call-in information for site locations/attendees |  |  |  | 2 | weeks | -14
Receive Speakers presentation as a backup |  |  |  | 2 | weeks | -14
Provide Site locations with preliminary attendance numbers |  |  |  | 2 | weeks | -14
Determine main facilitator/host for webinar |  |  |  | 2 | weeks | -14
1 Week out
Send sign in sheets/reimbursement forms to site locations |  |  |  | 1 | week | -7
Day of Webinar
Sign into Webinar software 30 minutes prior to webinar start | [5 empty] | 0
Confirm everyone's connection/monitor audio/change presenters/answer questions via chat box | [5 empty] | 0
After the Webinar
Administrative close out of webinar (receive sign-in sheets, processing payment reimbursements, post presentations to website, follow emails to attendees, monitor online post-test, process post-test for transcripts) | [5 empty] | 1900-01-20
Formulas:
Due Date = C5-([Target Range]*30)

## Seminar Sample
Planning Timeline for One-day Seminar
Committee: | Cool Committee
Title of Event: | Awesome Event
Proposed Event Date: |  | 2022-07-01 |  | (MM/DD/YY)
Location type for Seminar: |  |  | Contract space (Hotel or conference center) |  | X | Free space (Utility/Consultant or donated space)
Registration Fee: | 50 | (member fee) |  | Target Attendance: | 45
| 75 | (non-member fee) |  |  | 5
Budget/Projected Net Income*: |  |  | 656.25
* 25% of revenue generated - rough budget projection only. Use budget spreadsheet for final predictions
Task |  |  |  |  | Target Range |  | Due Date | Assigned Committee Member
6-9 Months out
Select date (Check Section calendar to verify no conflicts) |  |  |  |  | 9 | months | 2021-10-04
Determine location (contract vs. free) |  |  |  |  | 9 | months | 2021-10-04
Negotiate any contracts for Room rental, AV, Lodging (if applicable) |  |  |  |  | 8 | months | 2021-11-03
Select caterer and negotiate contract (if different then facility) |  |  |  |  | 8 | months | 2021-11-03
Send all contracts to Association for signature |  |  |  |  | 8 | months | 2021-11-03
Determine Topic |  |  |  |  | 8 | months | 2021-11-03
Confirm Speakers/Presenters |  |  |  |  | 7 | months | 2021-12-03
Receive abstracts from speakers |  |  |  |  | 6.25 | months | 2021-12-25 12:00
Submit joint CPE form for consideration |  |  |  |  | 6 | months | 2022-01-02
3-6 Months out
Prepare draft flyer/brochure |  |  |  |  | 5 | months | 2022-02-01
Send information to Exec Director for registration site and conduct testing |  |  |  |  | 5 | months | 2022-02-01
Receive CPE approvals |  |  |  |  | 4.5 | months | 2022-02-16
Finalize flyer/brochure and open registration |  |  |  |  | 4 | months | 2022-03-03
Promote event via e-Newsletter, Magazine, Website, Social Media |  |  |  |  | 4 | months | 2022-03-03
Mail flyers (if applicable) |  |  |  |  | 4 | months | 2022-03-03
Monitor registration and continue to promote event |  |  |  |  | 3 | months | 2022-04-02
1-2 Months out
Re-confirm local arrangements |  |  |  |  | 2 | months | 2022-05-02
Assign moderator/volunteer positions for on-site tasks |  |  |  |  | 1 | month | 2022-06-01
Confirm AV needs/equipment |  |  |  |  | 1 | month | 2022-06-01
Receive presentations from speakers |  |  |  |  | 1 | month | 2022-06-01
2 Weeks out
Print agenda/handouts |  |  |  |  | 2 | weeks | 2022-06-17
Acquire Speaker Bios for introductions |  |  |  |  | 2 | weeks | 2022-06-17
1 Week out
Send final attendee numbers to caterer |  |  |  |  | 1 | week | 2022-06-24
Receive any registration materials from Exec Director if unable to attend |  |  |  |  | 1 | week | 2022-06-24
Link to Eventfull App sent to volunteers for scanning |  |  |  |  | 1 | week | 2022-06-24
Day of Seminar
Ensure volunteers fulfill their assigned duties | [6 empty] | 2022-07-01
Conduct mini-training with volunteers in charge of scanning duties | [6 empty] | 2022-07-01
Review and sign any location/catering charge for seminar | [6 empty] | 2022-07-01
After the Seminar
Confirm with Executive Director there were no changes to program and all badges were properly scanned |  |  |  |  | 1 | week | 2022-07-08
Submit Invoice Payment Requests for all expenses |  |  |  |  | 1 | week | 2022-07-08
Send final presentations and event photos to Exec Director for posting online |  |  |  |  | 1 | week | 2022-07-08
Send Thank you notes to speakers |  |  |  |  | 1 | week | 2022-07-08
Formulas:
Due Date = C5-([Target Range]*30)
Due Date = C5+([Target Range]*7)

## Webinar Sample
Planning Timeline for Webinars
Committee: | Awesome Committee
Title of Event: | How to Plan a Webinar
Proposed Event Date: |  | 2022-07-01 |  |  | (MM/DD/YY)
Determine type of webinar: |  |  | Site locations | X | Online Only |  | Hybrid
Registration Fee: | 25 | (member fee) |  |  | Target Attendance: |  | 40
| 40 | (non-member fee) |  |  |  |  | 5
Finalize Budget/Projected Net Income: |  |  |  | 750
Task | [5 empty] | Target Range |  | Due Date | Assigned Committee Member
3-6 Months out
Determine Topic | [5 empty] | 6 | months | 2022-01-02
Confirm Speakers/Presenters | [5 empty] | 5.25 | months | 2022-01-24 12:00
Receive abstracts from speakers | [5 empty] | 4.5 | months | 2022-02-16
Site locations contacted to confirm availability (if applicable) | [5 empty] | 4 | months | 2022-03-03
Submit abstract forms for CPE consideration | [5 empty] | 4 | months | 2022-03-03
Prepare flyer/brochure | [5 empty] | 3.5 | months | 2022-03-18
Create registration site and conduct testing | [5 empty] | 3.5 | months | 2022-03-18
2-3 Months out
Receive CPE approvals | [5 empty] | 3 | months | 2022-04-02
Open registration | [5 empty] | 3 | months | 2022-04-02
Promote event via e-Newsletter, Magazine, website | [5 empty] | 3 | months | 2022-04-02
Mail flyers (if applicable) | [5 empty] | 2.5 | months | 2022-04-17
Create webinar powerpoint template for use by speakers | [5 empty] | 2.5 | months | 2022-04-17
1-2 Months out
Re-confirm local arrangements (if applicable) | [5 empty] | 2 | months | 2022-05-02
Schedule Test run with speakers | [5 empty] | 1 | month | 2022-06-01
Schedule Test run with site locations | [5 empty] | 1 | month | 2022-06-01
Receive post-test questions from Speakers (Required if CPE's approved) | [5 empty] | 1 | month | 2022-06-01
Create post-test for online attendees (Required if CPE's approved) | [5 empty] | 1 | month | 2022-06-01
2 Weeks out
Send out Call-in information for site locations/attendees | [5 empty] | 2 | weeks | 2022-06-17
Receive Speakers presentation as a backup | [5 empty] | 2 | weeks | 2022-06-17
Provide Site locations with preliminary attendance numbers | [5 empty] | 2 | weeks | 2022-06-17
Determine main facilitator/host for webinar | [5 empty] | 2 | weeks | 2022-06-17
1 Week out
Send sign in sheets/reimbursement forms to site locations | [5 empty] | 1 | week | 2022-06-24
Day of Webinar
Sign into Webinar software 1 hour prior to webinar start | [7 empty] | 2022-07-01
Confirm everyone's connection/monitor audio/change presenters/answer questions via chat box | [7 empty] | 2022-07-01
After the Webinar
Administrative close out of webinar (receive sign-in sheets, processing payment reimbursements, post presentations to website, follow emails to attendees, monitor online post-test, process post-test for transcripts) | [7 empty] | 2022-07-22
Formulas:
Due Date = C5-([Target Range]*30)